## DevOps Timeline (12 Weeks)
Week | Phase | Activity | Description | Owner
Week 1 | Planning | Requirement Finalization | Finalize scope for JAVA, CMA, SQL automation | DevOps + C2M SME
Week 2 | Setup | Access Setup | SSH, Azure DevOps, DB, WebLogic access | Infra + DevOps
Week 3 | Script | JAVA Automation | Refactor applyCM.sh with logging | DevOps
Week 4 | Script | CMA Automation | Automate TPW, batch jobs, flush | DevOps + C2M SME
Week 5 | Script | SQL Standardization | Prepare SQL execution + rollback | DBA + DevOps
Week 6 | Pipeline | Pipeline Design | Design Azure DevOps pipelines | DevOps
Week 7 | Pipeline | JAVA Pipeline | Build + Deploy + Restart automation | DevOps + WebLogic
Week 8 | Pipeline | SQL Pipeline | Automate SQL execution | DevOps + DBA
Week 9 | Pipeline | CMA Pipeline | Automate CMA deployment | DevOps
Week 10 | Enhancement | Multi-node + Email | 2-node logic + notifications | DevOps + WebLogic
Week 11 | Testing | Testing & Fix | End-to-end testing, bug fixing | DevOps + QA
Week 12 | Release | UAT & PROD | Deployment + KT | DevOps + All Teams